## Sheet1
Work Activity Base Production Rates
Item | Unit | Base Rate | Metric Base Rate
Grade Items |  |  |  |  | Assumptions/Notes:
Mobilization | Days | 5
Clearing & Grubbing | Acres | 2.625 | 1.0623
Demo. Of Buildings | Each | 1 |  |  | A.) Production rates are units/day based on an 8 hr. day unless otherwise noted,
Asbestos Rem.(Res./Small Commercial) | Days | 4 |  |  | such as by Days or POUR.
Asbestos Rem.(Large Commercial) | Days | 10
Demo. Of Asphalt Pave. | S.Y. | 1500 | 1254.255 |  | B.) Production rates are based on the average of rates from five other nearby states with
Sawcut Pavement | L.F. | 800 | 243.84 |  | assumed similar work conditions. States referenced were Kentucky, Tennessee,
Remove Curb& Gutter | L.F. | 600 | 182.88 |  | New Jersey, West Virginia, and Georgia.
Remove Exist. DI/Manhole & Assoc. Pipe | Each | 6
Temporary Detour | Days | 6
Roadway Excavation | C.Y. | 2000 | 1529.11 |  | C.) RS Means Rates and VDOT records were also used as a reference when wide variation
Excavation Small/Irregular Area Projects | C.Y. | 850 | 649.8718 |  | was found between different state's rates or if little information was available for a specific
Excavation - Large quantity projects | C.Y. | 5000 | 3822.775 |  | work item.
Drainage Corrug.Metal 18" | L.F. | 205 | 62.484
Drainage Concrete Pipe 15" | L.F. | 168 | 51.2064 |  | D.) Scheduler should contact Roadside Development for planting restrictions and time
Drainage Conc. Pipe 18" | L.F. | 144 | 43.8912 |  | estimates. Landscaping rates are typically controlled by the planting season.
Drainage Conc. Pipe (24" to 54") | L.F. | 72 | 21.9456
Drainage Conc. Pipe (60 in. & greater) | L.F. | 48 | 14.6304 |  | E.) Production rates were verified by VDOT project records as much as possible and are
Inlets/Manholes | Each | 1.5 |  |  | intended for temporary use until the final database is produced at the conclusion of
Minor Excavation (Drainage Structures) | C.Y. | 250 | 191.1387 |  | a more intensive three year study of historical data specific to VDOT.
Box Culverts, Class A Conc. | C.Y. | 20 | 15.2911
Box Culverts, Cast in Place | L.F. | 5 | 1.524 |  | F.) Sensitivity Factors are estimated according to their effect on normal production.
Box Culverts, Precast | L.F. | 20 | 6.096 |  | If the scheduler disagrees with the factors for a specific application, he or she should
Retaining Walls, Cast in Place | L.F. | 5 | 1.524 |  | develop a unique value. For example excavation rates will be widely variable
Major Retaining Walls | S.F. | 210 | 19.5096 |  | considering the range of topography between the Bristol and Hampton Road Districts.
Sub-grade Stabilization | S.Y. | 8000 | 6689.36 |  | If the average figure sounds off for your project, consider making additional calculations
Aggregate Base | Tons | 1360 | 1233.792 |  | based on the excavation equipment most likely to be used.
Aggregate Base Small/Irregular Projects | Tons | 680 | 616.896
Drainage Blanket | Tons | 1200 | 1088.64
Asphalt Base | Tons | 1175 | 1065.96 |  | G.) Utility 12" and drainage pipes include excavation/backfill for good soil conditions in a 4-5 ft.+/-
Asphalt Intermediate | Tons | 750 | 680.4 |  | trench. Additional time for excavation should be estimated by the scheduler
Asphalt Surface | Tons | 500 | 453.6 |  | for unfavorable conditions.
Milling/Flexible Pavement Planing (Max. 2") | S.Y. | 3000 | 2508.51
Curb & Gutter (Machine Placed) | L.F. | 800 | 243.84 |  | H.) Several of the adjustment factors should have similar impacts on production,
Curb & Gutter (Hand Placed) | L.F. | 400 | 121.92 |  | so generally it is recommended not to reduce the base quantity by more than 2 factors except
Curb& Gutter Radial (Hand Placed) | L.F. | 150 | 45.72 |  | in special circumstances.
Concrete Entrance | S.Y. | 80 | 66.8936
Sidewalk | S.F. | 1550 | 143.9997 |  | I.) Consult with your Traffic Engineering Section for production rates for specialty
Concrete Driveway | S.Y. | 150 | 125.4255 |  | items to make sure you account for the necessary review and fabrication times.
Entrance Pavement | S.Y. | 100 | 83.617
Barrier Walls, Slip Form | L.F. | 630 | 192.024
Concrete Repair | S.Y. | 30 | 25.0851
Concrete Paving | S.Y. | 2500 | 2090.425
Slurry Seal | S.Y. | 8000 | 6689.36 |  |  | Base Rate Adjustment Factors
Seeding | Acres | 2.5 | 1.0117
Fencing | L.F. | 1000 | 304.8
Fine Grading | S.Y. | 2000 | 1672.34 |  | Factors | Adjustment for Noted Conditions
Lime Stabilization | S.Y. | 6000 | 5017.02 |  | Location | Rural = 1.0 | Small City = 0.85 | Big City = .75
Shoulder Construction | L.F. | 500 | 152.4 |  | Traffic Conditions | Light = 1.0 | Moderate = .88 | High = .70
Slope Protection | C.Y. | 100 | 76.4555 |  | Complexity | Low = 1.0 | Medium = .85 | High = .70
Underdrain | L.F. | 1500 | 457.2 |  | Soil Conditions | Good = 1.0 | Fair = .85 | Poor = .65
Underdrain Outlet/Endwall | Each | 8 |  |  | Quantity of Work | Large = 1.0 | Medium = .88 | Small = .75
Utility 12" Ductile Iron | L.F. | 105 | 32.004
Utility 12" PVC | L.F. | 320 | 97.536
Directional Drilling | L.F. | 50 | 15.24 |  | Example Production Rate Calculation for Roadway Excavation:
Conditions: Rock Excavation around moderate traffic.
Traffic Items |  |  |  |  | Calculation: 2000 C.Y. x .65 x .88 = 1144 C.Y. per day
Initial Traffic Control | Days | 2
Ordering Signal Equip. | Days | 30 |  |  | Example Production Rate Calculation for Bridge Footing:
Major Traffic Signals | Days/Intersec. | 40 |  |  | Conditions: Rural Bridge Replacement, Traffic Detoured, Small Two Lane structure
Pavement Markings | L.F. | 10000 | 3048 |  | Calculation: 20 C.Y. x 1.0 x .75 = 15 C.Y.
Stop Bars, etc. | L.F. | 500 | 152.4
Arrows/Letters | Each | 50
Order Sign Material | Days | 60
Order Overhead Sign Struct. | Days | 80
Erecting Overhead Signs | Days | 10
Erecting Signs | S.F. | 1000 | 92.903
Ordering Lighting Material | Days | 60
Erecting Lighting | Days/support | 3
Guardrail | L.F. | 1500 | 457.2
Guardrail Terminals | Each | 2
Order Impact Attenuators | Days | 30
Install Impact Attenuator | Each | 3
Electrical Conduit | L.F. | 400 | 121.92
Electrical Wire | L.F. | 3500 | 1066.8
Precast concrete barrier | L.F. | 800 | 243.84
Lighting, Total Installation Lumin. | Each | 2
Phasing Allowance | Days/Phase | 3
Bridge Items
| Unit | Base Rate
MOT Setup
Impact Attenuators | EA | 2
Median Barrier - Install | LF | 800 | 243.84
Removing Exst. Guardrail | LF | 1500 | 457.2
Shoulder Improvements | LF | 500 | 152.4
Signs, Install Small (Sheet) | EA | 30
Temporary Detour Bridge - Install | Days | 13
Traffic Control Setup | Days | 2
Excavation/Demolition
Cofferdam | Days | 15
Dismantle/Remove Exst. Concrete Deck | SY | 275 | 229.9468
Dismantle/Remove Exst. Structure | SY | 50 | 41.8085
Minor Excavation | CY | 250 | 191.1387
Sheet Piling - Drive | SF | 500 | 46.4515
Structure Excavation | CY | 300 | 229.3665
CBR30 Backfill/Compact Abutment | TON | 100 | 90.72
Substructure Items
Drilled Shafts | EA | 0.3
Epoxy Injection Crack Repair | LF | 80 | 24.384
Reinforcing Steel | TON | 2.5 | 2.268
Retaining Walls (CIP) | SF | 400 | 37.1612
Riprap - Dumped | TON | 700 | 635.04
Riprap - Grouted | TON | 50 | 45.36
Riprap - Machine Placed | TON | 250 | 226.8
Slope Protection - Concrete | SY | 750 | 627.1275
Steel Piles - Prebored | LF | 250 | 76.2
Steel Piles - Driven | LF | 400 | 121.92
Concrete Piles - 8" to 14" | LF | 300 | 91.44
Concrete Piles - 24" to 30" | LF | 325 | 99.06
Substructure Footings - Form and Place | CY | 20 | 15.2911
Substructure Neatwork - Form and Place | CY | 10 | 7.6456
Substructure Footing - Place Seal | CY | 15 | 11.4683
Superstructure Items
Approach Slabs | DAY | 5
Beam Repairs - Concrete Beam End | EA | 0.25
Beam Repairs (Steel) - Bolted | EA | 0.5
Beam Repairs (Steel) - Welded | EA | 1
Bridge Deck - Form & Place Reinf. Steel | SY | 50 | 41.8085
Bridge Deck - Overlay | SY | 500 | 418.085
Bridge Deck - Pour New | SY | 850 | 710.7445
Bridge Deck Grooving | SY | 550 | 459.8935
Bridge Deck - Sidewalk/Raised Median | LF | 80 | 24.384
CIP Conc. Slab Span - Install Falsework | SF | 250 | 23.2258
CIP Conc. Slab Span - Pour | CY | 10 | 7.6456
Concrete Diaphragms - Form & Pour | CY | 11 | 8.4101
Concrete Removal - Sub/Super Patch | SY | 15 | 12.5426
Concrete Removal - Type B Patch | SY | 50 | 41.8085
Concrete Removal - Type C Patch | SY | 10 | 8.3617
Concrete Surface Color Coating | SY | 100 | 83.617
Expansion Dam | EA | 4
Expansion Joint Reconstruction | LF | 25 | 7.62
Expansion Joint Removal | LF | 250 | 76.2
Expansion Joint Sealer | LF | 450 | 137.16
Milling (Concrete - per 1/2" depth) | SY | 1600 | 1337.872
Parapet - Hand Formed | LF | 50 | 15.24
Parapet - Slip Formed | LF | 200 | 60.96
Metal Rail Parapet | LF | 100 | 30.48
Kansas Corrall Parapet | LF | 20 | 6.096
Pedestrian Fence | LF | 7 | 2.1336
Prestressed Conc. Beam Erection | LF | 400 | 121.92
Shotcrete | SY | 65 | 54.3511
Struct. Steel Surface Prep. (Method 1) | SF | 3000 | 278.709
Struct. Steel Surface Prep. (Method 2) | SF | 240 | 22.2967
Struct. Steel Surface Prep. (Method 3) | SF | 600 | 55.7418
Struct. Steel Surface Prep. (Method 4) | SF | 200 | 18.5806
Struct. Steel Surface Prep. (Method 5) | SF | 1100 | 102.1933
Struct. Steel Surface Prep. (Method 6) | SF | 6000 | 557.418
Struct. Steel Surface Prep. (Method 7) | SF | 7500 | 696.7725
Structural Steel - Painting (per coat) | SF | 2000 | 185.806
Structural Steel Erection | TON | 10 | 9.072
Structural Steel Erection | LF | 200 | 60.96
Timber Bridge Deck | SF | 200 | 18.5806
Finishing Items/MOT Teardown
CIP Conc. Slab Span - Remove Falsework | SF | 500 | 46.4515
Median Barrier - Remove | LF | 800 | 243.84
Sheet Piling - Pull | SF | 500 | 46.4515
Temporary Detour Bridge - Remove | Days | 4
Traffic Control Teardown | Days | 2
Concrete Curing |  | Cure days/Pour
Deck overlays - Assume 20 CY of material placement per day
LMC | POUR | 5
HESLMC | POUR | 3
VESLMC | POUR | 1
New Construction
Substructure Footings | POUR | 2
Substructure Neatwork | POUR | 5
Bridge Deck Concrete | POUR | 7
Parapet | POUR | 7
Component Level Production Rates |  |  |  | (Recommended for use at Field Inspection before all quantity details are known)
Item | Unit | #Days |  | Special Notes:
Abutments | Days | 8 |  | Add 1 day for each 400' of piles. Add time for cofferdam/structure exc. Includes normal curing conditions.
Piers or Bents | Days | 15 |  | Add 1 day for each 400' of piles. Add time for cofferdam/structure exc. Includes normal curing conditions.
Concrete Deck Span 20'-40' | Days | 15 |  | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 41'-60' | Days | 21 |  | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 61'-80' | Days | 27 |  | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 81'-100' | Days | 33 |  | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 101'-120' | Days | 39 |  | Includes form, rebar, pour, normal cure time.
Concrete Deck Span 121'-140' | Days | 45 |  | Includes form, rebar, pour, normal cure time.
Steel Beams (Plate Girder) | Each |  |  | Add 2-3 days/span for diaphragms
Steel Beams (Rolled Steel) | Each |  |  | Add 1 day/span for diaphragms
Concrete Beams | Each |  |  | Add 2-3 days/span for diaphragms
New Bridge Construction | L.F.
1 station (100 ft.) of 12 ft. lane roadway rural or new construction | Days | 2 |  | Includes clearing & grubbing, grading, pavement structure, guardrail, seeding, and light drainage work.
1 station (100 ft.) of 12 ft. lane roadway urban or widening work | Days | 4 |  | Includes above plus curb & Gutter, Drainage, Utilities, and items commonly encountered in urban work.
Note: Component Level Production Rates are recommended for estimating time at the field inspection or early planning stages before quantities are known.